AgentGuard

(working name)

Project Roadmap

From idea to launch: phases, deliverables and how we build it

| Item | Detail |
| --- | --- |
| Prepared for | Pratik Batha – System Memo |
| Prepared by | Ulises Romano, Lead Software Developer |
| Version / date | v1.0 – October 2026 |
| Planned duration | About 30 weeks to public launch, then ongoing improvement |
| Companion document | AgentGuard – Core Functions, Challenges and Solutions |

Table of Contents

When Word asks to update fields, choose Yes to fill in the page numbers.

1. Overview

1.1 Guiding principles

1.2 Phases at a glance

2. Scope

2.1 Included in version 1

2.2 Planned after launch

2.3 Not planned for now

3. Architecture

3.1 Components

3.2 Standard action event

3.3 Decision flow

3.4 Connection methods and rollout

4. Technology Stack

5. Team and Ways of Working

5.1 Ways of working

6. Timeline

6.1 Sprint plan

7. Phase Details

Phase 0 – Preparation (before week 1)

Phase 1 – Discovery, design and architecture (weeks 1–4)

Phase 2 – Core platform: See & Control (weeks 5–12)

Phase 3 – Gateways and private beta (weeks 13–18)

Phase 4 – Secure execution and team features (weeks 19–24)

Phase 5 – Hardening and launch (weeks 25–30)

Phase 6 – After launch (week 31 onward)

8. Feature Backlog

9. Data Model and API

9.1 Main data

9.2 Public API

10. Security and Data Protection

11. Quality and Operations

11.1 Testing

11.2 Operations

12. Go-to-Market and Launch

12.1 First customers

12.2 Launch plan

12.3 Business model (to be validated in beta)

12.4 Positioning

13. Risks and Mitigations

14. Goals

15. Open Decisions

Appendix – Glossary

# 1. Overview

AgentGuard is a control layer for AI agents. It lets a business see what its connected agents do and say, control which tools they use, limit spending, require human approval for risky actions, and block any agent instantly at every checkpoint, across n8n, Make, LangChain, the OpenAI and Claude SDKs and custom code.

This roadmap describes how the product will be built: phases, scope, architecture, security, quality, launch and the main decisions. The companion document explains the product idea, the challenges and the solutions in detail.

## 1.1 Guiding principles

- Deliver value early: an observe-only version is useful from the first weeks of beta.

- Honest coverage: we always show which actions are enforced, cooperative or uncovered.

- Safety first for irreversible actions: money, deletion and publishing move to enforced checkpoints wherever a connector exists.

- Build on open standards (MCP, OpenTelemetry, OpenAI-compatible APIs) to keep connectors thin.

- Focused scope: popular platforms and high-value actions first; more connectors follow customer demand.

## 1.2 Phases at a glance

| Phase | Name | Weeks | Main outcome |
| --- | --- | --- | --- |
| 0 | Preparation | Before week 1 | Company and contract ready, accounts and tools set up |
| 1 | Discovery, design and architecture | 1–4 | Validated requirements, designs, architecture, security design |
| 2 | Core platform: See & Control | 5–12 | Registry, observe mode, rules, approvals, limits; n8n, Make, SDKs, API |
| 3 | Gateways and private beta | 13–18 | AI-model gateway, MCP gateway, framework integrations; beta users |
| 4 | Secure execution and team features | 19–24 | Credential vault, first connectors, roles, audit export |
| 5 | Hardening and launch | 25–30 | Independent security test, reliability, documentation, public launch |
| 6 | After launch | 31 onward | Stabilization, more connectors and integrations, smart features |

Week 1 starts once the company registration is complete and the development agreement is signed. All dates are planning targets and will be reviewed at the end of each phase.

# 2. Scope

## 2.1 Included in version 1

Items marked “if time allows” are planned for version 1 but may move to shortly after launch (see the backlog in section 8).

- Agent registry, identities, tokens, kill switch

- Observe mode and live activity log with audit trail

- Rules: tool permissions, conditions, unknown-tool protection, cumulative limits

- Human approval (dashboard, Slack, secure email page) locked to the exact action

- AI-model cost budgets and real-money limits for known actions

- Response checkpoint for agent replies (promises, prices, personal data)

- Connections: REST check API, Python & TypeScript SDKs, n8n guarded tool nodes, Make app, AI-model gateway, MCP gateway; LangGraph and OpenAI Agents SDK integrations (if time allows)

- Credential vault with first connectors: Stripe, Slack, HubSpot (Shopify and Gmail when their reviews are approved, possibly after launch)

- Coverage score; rule templates and policy replay (if time allows)

- Organizations, roles, audit export

## 2.2 Planned after launch

- CrewAI and Claude Agent SDK integrations; Zapier; more vault connectors (Salesforce, Zendesk, Outlook, databases)

- Single sign-on (SAML), user provisioning, longer retention options

- Rule suggestions from approval history, plain-English rules, earned limits, anomaly detection

- Partial discovery of unregistered agents

- Agency workspaces and client views; oversight reports

- Regional hosting (e.g. EU), customer-hosted checkpoints

## 2.3 Not planned for now

- Building or hosting customers’ agents (we govern agents, we don’t build them)

- Regulated data areas (e.g. healthcare records, trading) until proper compliance is in place

- Screen-level control of browser or computer-use agents

- Native mobile apps (responsive web and Slack/email approvals instead)

# 3. Architecture

## 3.1 Components

┌──────────────────────────────────────────────┐

│      CONTROL CENTER (web app + API)          │

│ Registry · Rules · Approvals · Budgets       │

│ Activity & audit · Coverage · Alerts         │

└───────────────────▲──────────────────────────┘

│ decisions / events

┌───────────┐    ┌──────────────┴───────────────────────┐    ┌─────────────┐

│ Any agent │───▶│            CHECKPOINTS               │───▶│ Real world  │

│ n8n, Make │    │ Enforced:  AI-model gateway,         │    │ AI models   │

│ LangGraph │    │            MCP gateway, vault        │    │ Stripe,Slack│

│ SDKs ...  │    │ Cooperative: SDK, n8n/Make, check API│    │ CRM, DB ... │

└───────────┘    └──────────────────────────────────────┘    └─────────────┘

▲  ALLOW / BLOCK / ASK A HUMAN

Authorized approver (Slack / secure email / dashboard)

| Component | Responsibility |
| --- | --- |
| Web dashboard | Agents, rules, approvals inbox, activity, budgets, coverage, settings |
| Core API | Organizations, users, agents, tokens, rules, events; public API |
| Decision service | Evaluates each action against rules, limits and risk; returns allow / block / ask a human |
| Rule engine | Proven policy engine (OPA or Cedar); rules created in the visual builder or from templates |
| Limits service | Real-time counters for cost and money: per action, customer, agent and period; reserve-then-settle |
| Approval workflow | Durable pending state, notifications, approver checks, timeouts, escalation, resume |
| AI-model gateway | OpenAI/Anthropic-compatible proxy: cost metering, model limits, response checkpoint, visibility of what the agent read |
| MCP gateway | Proxy for MCP tool servers; tool permissions and argument rules |
| Credential vault | Encrypted storage of customer credentials; executes approved actions exactly once |
| Event pipeline & audit | Stores every action, decision and approval; tamper-evident audit log |
| Notifications | Slack app, email, webhooks |

## 3.2 Standard action event

Every connection method converts what it sees into one format, so rules are written once for all agents.

{

"event_id": "evt_01H...",          "agent_id": "support-bot-01",

"source": "vault | ai_gateway | mcp_gateway | sdk | n8n | make | api",

"enforcement": "enforced | cooperative",

"action": "payment.refund",        "resource": "stripe:charge/ch_123",

"params": { "amount": 250, "currency": "usd", "customer": "cus_9" },

"params_fingerprint": "sha256:...", "idempotency_key": "ch_123:payment.refund",

"untrusted_input_seen": true,       "risk": "high",

"decision": "ASK_HUMAN",            "rules": ["refund_limit", "weekly_customer_cap"]

}

## 3.3 Decision flow

- The agent attempts an action; a checkpoint catches it and creates the standard event.

- Duplicate check: a key built from the action itself (e.g. order + action type) is compared with recent actions; if it already ran, the earlier result is returned instead of running it again.

- Checks: agent active? tool known and allowed? per-action and cumulative limits? rules? risk?

- Result: allow, block (with reason) or ask a human (approval ID returned; agent receives “pending”).

- Approval is locked to the parameter fingerprint; only authorized approvers can decide; timeout = reject or escalate.

- Enforced checkpoints execute exactly the approved action once; cooperative ones report completion.

- Everything is written to the audit log.

## 3.4 Connection methods and rollout

| Method | Level | Customer effort | Phase |
| --- | --- | --- | --- |
| REST check API + webhooks | Cooperative | One HTTP call | 2 |
| Python & TypeScript SDKs | Cooperative | A few lines of code | 2 |
| n8n guarded tool nodes + approval pattern | Cooperative | Use our tool nodes in the AI Agent | 2 |
| Make app + two-scenario approval pattern | Cooperative | Add our module | 2 |
| AI-model gateway | Enforced* | Change the API base URL | 3 |
| MCP gateway | Enforced* | Point the agent to our MCP address | 3 |
| LangGraph, OpenAI Agents SDK integrations | Cooperative | Install integration | 3 |
| OpenTelemetry import | Visibility only | Add exporter address | 3 |
| Credential vault + connectors | Enforced* | Connect accounts; agent uses our token | 4 |

* Enforced checkpoints only hold if the agent has no other way to reach the tool: the real AI-provider keys, MCP-server credentials and tool credentials must be stored only in AgentGuard, and old keys rotated.

# 4. Technology Stack

| Layer | Choice | Reason |
| --- | --- | --- |
| Frontend | Next.js (React, TypeScript), Tailwind, shadcn/ui | Fast to build, modern UI |
| Backend API | Python FastAPI or Node (decided in Phase 1) | Strong AI ecosystem, async |
| Gateways | Go or Node streaming proxy | Low latency, streaming support |
| Rule engine | OPA (Rego) or AWS Cedar | Proven, fast, auditable |
| Database | PostgreSQL (row-level security per organization) | Reliable; customer separation |
| Counters / cache | Redis | Real-time limits and rule cache |
| Workflows | Temporal or a durable queue | Approvals, timeouts, retries |
| Authentication | Managed provider (Clerk / Auth0 / WorkOS) | Secure login, MFA, SSO later |
| Secrets | Cloud key management with envelope encryption | Safe storage of customer credentials |
| Infrastructure | AWS (containers), Terraform | Scalable, reproducible |
| CI/CD | GitHub Actions | Automated tests and deployment |
| Monitoring | OpenTelemetry, Grafana/Prometheus or Datadog, Sentry | Watch our own platform |
| Notifications | Slack API, transactional email | Approvals and alerts |

# 5. Team and Ways of Working

| Role | Who | Responsibilities |
| --- | --- | --- |
| Product owner / CEO | Pratik Batha | Vision, priorities, customer interviews, design partners, marketing, phase acceptance |
| Lead developer / architect | Ulises Romano | Architecture, core platform, gateways, vault, security design, code review, DevOps |
| Backend / integrations developer | To be added from Phase 2 | n8n/Make, SDKs, framework integrations, connectors, tests |
| UI/UX designer | Pratik’s designer | Research, user flows, design system, dashboard, website |
| Independent security tester | External | Security test of web app, API, gateways and vault (Phase 5) |
| Marketing / community | Pratik + System Memo | Content, webinars, waitlist, launch |

## 5.1 Ways of working

- Two-week sprints with a demo to Pratik at the end of each sprint

- Short written daily update; weekly progress note (done, next, risks, decisions needed)

- Tasks in Linear / Jira / GitHub Projects; designs in Figma

- Code in a company-owned GitHub organization; reviews required before merging

- Each phase ends with a review and written acceptance before the next phase starts

# 6. Timeline

| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ph 1 Discovery & design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ph 2 See & Control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ph 3 Gateways & beta |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ph 4 Secure execution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ph 5 Hardening & launch |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ph 6 After launch |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Connector reviews (Google, Shopify) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Design partners / private beta |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Marketing build-up |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

## 6.1 Sprint plan

| Sprint | Weeks | Phase | Sprint goal | Demo |
| --- | --- | --- | --- | --- |
| S1 | 1–2 | 1 | Interviews, user flows, architecture draft, environments and CI | Flows and architecture walkthrough |
| S2 | 3–4 | 1 | Final designs, security design, technical prototypes; app-review preparation | Clickable prototype; prototype results |
| S3 | 5–6 | 2 | Login, organizations, agent registry, tokens, event API, observe mode | Agent connected; activity visible |
| S4 | 7–8 | 2 | Rule engine, visual builder, unknown-tool protection, cumulative limits, idempotency | Rule blocks a test action; duplicate prevented |
| S5 | 9–10 | 2 | Approvals (dashboard, Slack, secure email), approver checks, parameter locking, timeouts | Approval flow end to end |
| S6 | 11–12 | 2 | n8n guarded tool nodes, Make app, Python/TS SDKs, dashboard v1, baseline load test | n8n agent refund paused → approved → completed |
| S7 | 13–14 | 3 | AI-model gateway: streaming, cost budgets, model limits | Cost tracked; budget stops agent |
| S8 | 15–16 | 3 | Response checkpoint, MCP gateway; private beta starts | Risky reply held; MCP tool denied |
| S9 | 17–18 | 3 | LangGraph + OpenAI Agents SDK integrations, OpenTelemetry import, coverage score | Framework demos; coverage view |
| S10 | 19–20 | 4 | Credential vault, Stripe connector, exact-once execution | Refund via vault with approval |
| S11 | 21–22 | 4 | Slack and HubSpot connectors; Shopify/Gmail if approved; reserve-then-settle | Connectors demo |
| S12 | 23–24 | 4 | Roles, audit export, templates, policy replay | Team roles; replay of past activity |
| S13 | 25–26 | 5 | Independent security test; load and failure tests | Test findings and fix plan |
| S14 | 27–28 | 5 | Security fixes, monitoring, backups, documentation site | Production readiness review |
| S15 | 29–30 | 5 | Production launch, website, onboarding, beta-to-customer conversion | Public launch |

# 7. Phase Details

## Phase 0 – Preparation (before week 1)

Goal: Remove every blocker before development starts.

### Work

Company and agreement

- Company registration completed

- Development agreement signed by the registered company: scope, phases, acceptance process, IP ownership, confidentiality, change process

- Product name, domain and trademark check

Accounts and tools

- Company-owned GitHub, cloud, domain, email, Figma, task tracker, chat workspace

- AI-provider accounts and test accounts for Stripe, Slack, HubSpot, Shopify, Google

- Shared password manager

### Deliverables

- Signed agreement

- All accounts ready with access granted

- Kick-off meeting

### Done when

- Agreement signed and access working

## Phase 1 – Discovery, design and architecture (weeks 1–4)

Goal: Confirm what customers need and fix the design and architecture before heavy coding.

### Work

Product discovery

- Review Pratik’s product document and competitors

- Interview 8–12 potential customers (agencies, n8n/Make builders, e-commerce, AI startups)

- Choose the first use case and first customer group

- Product requirements document and prioritized backlog

Design

- User flows: connect agent, observe, create rule, approve, view activity, set limits, kill switch

- Figma designs, design system, Slack approval message, secure email page

- Clickable prototype tested with 3–5 users

Architecture and security

- Architecture document, data model, standard action event, API design

- Security design and threat model, including approval loopholes (parameter locking, duplicates, splitting, approver identity)

- Technical decisions: backend language, rule engine, workflow engine, auth provider

- Prototypes: decision speed, n8n tool-node approval, Make two-scenario resume, streaming gateway

Early starts

- Prepare early for Google and Shopify reviews (developer accounts, verified domain, privacy policy, requirements including Gmail’s security assessment); submit as soon as a working connector exists, since reviews can take weeks to months

- Development environments, CI pipeline, coding standards

### Deliverables

- Requirements and backlog

- Designs and prototype

- Architecture and security design

- Working environments and CI

- App-review preparation done

### Done when

- Pratik accepts requirements, designs and architecture

## Phase 2 – Core platform: See & Control (weeks 5–12)

Goal: A working product that can observe and control n8n, Make and code-based agents with rules, limits and human approval.

### Work

Foundation

- Login, organizations, invitations

- Agent registry: tokens (scoped, expiring, revocable), status, kill switch

- Event API, observe mode, activity log, tamper-evident audit log

Rules and limits

- Rule engine and visual builder: tool permissions, parameter conditions, time windows

- Unknown tools default to “ask a human”

- Per-action and cumulative limits (per customer, resource, agent, period)

- Duplicate protection: keys built from the action itself; deliberate repeats need confirmation

Approvals

- Pending state, approval ID, timeouts, escalation

- Approval locked to the parameter fingerprint

- Dashboard inbox, Slack app with approver verification, secure email confirmation page

- Approval view: facts from connected systems first (fully available once vault connectors exist in Phase 4), agent explanation second

Connections

- REST check API and webhooks

- Python and TypeScript SDKs with resume helpers

- n8n guarded tool nodes for the AI Agent node and Wait-node approval pattern

- Make app with the two-scenario approval pattern

### Deliverables

- Working platform on staging

- n8n nodes, Make app, SDKs (early versions)

- API documentation draft

- Demo: n8n agent’s refund paused, approved in Slack, completed once

### Done when

- End-to-end demo accepted

- Approval loopholes covered by automated tests

## Phase 3 – Gateways and private beta (weeks 13–18)

Goal: Add enforced checkpoints for AI-model traffic and MCP tools, and put the product in front of real users.

### Work

AI-model gateway

- OpenAI- and Anthropic-compatible proxy with streaming

- Cost metering, AI-cost budgets, model limits, loop detection

- Response checkpoint: commitments, prices, personal data

- Tracking of untrusted content the agent has read (for risk rules)

MCP gateway

- Proxy for MCP tool servers; tool permissions and argument rules

Integrations and visibility

- LangGraph and OpenAI Agents SDK integrations with ready-made pause/resume

- OpenTelemetry import and run timeline

- Coverage score: enforced / cooperative / uncovered

Private beta

- 10–20 design partners from System Memo’s audience

- Weekly feedback calls, in-app feedback, bug triage

- Publish n8n nodes to the community

### Deliverables

- Gateways running in beta

- Two framework integrations (if time allows)

- Coverage score

- Active private beta

### Done when

- Design partners using the product weekly

- No critical issues open

## Phase 4 – Secure execution and team features (weeks 19–24)

Goal: Make important actions impossible to skip on connected tools (once their real keys are held only by AgentGuard), and add what teams need to use the product daily.

### Work

Credential vault

- Encrypted credential storage; OAuth and API-key connections

- Agents use AgentGuard tokens; vault executes approved actions exactly once

- Kill switch revokes all of an agent’s vault access

Connectors

- Stripe (refunds, charges), Slack (messages), HubSpot (contacts, deals)

- Submit Shopify and Gmail connectors for review; release when approved (design partners can use Shopify custom apps in the meantime)

- Reserve-then-settle for money limits

Team features

- Roles: owner, admin, approver, viewer; approval routing

- Audit export; data retention settings

- Rule templates; policy replay on past activity

### Deliverables

- Vault with first connectors

- Roles, audit export, templates, replay

### Done when

- Vault security design reviewed

- Beta partners using at least one vault connector

## Phase 5 – Hardening and launch (weeks 25–30)

Goal: Make the product safe, reliable and ready for customers, then launch.

### Work

Security

- Independent security test of web app, API, gateways and vault (tester booked during Phase 3); fix all high and critical findings

- Dependency, container and secrets scanning; rate limits; firewall rules

- Security page, privacy policy, terms of service with liability terms, data-processing agreement (legal review)

Reliability

- Load and failure tests (gateway down, database down, Slack down)

- Per-action failure behaviour verified

- Monitoring, alerts, backups with restore test, status page

Launch

- Documentation site with quick-starts for every connection method

- Website, onboarding emails, demo video

- Production launch; beta users move to production

### Deliverables

- Security test report and fixes

- Production environment

- Documentation and website

- Public launch

### Done when

- No open high or critical security findings

- Reliability tests passed

- Launch completed

## Phase 6 – After launch (week 31 onward)

Goal: Stabilize, learn from customers and extend the product.

### Work

Support

- Bug fixes, monitoring, customer support process

Extend

- CrewAI and Claude Agent SDK integrations; more connectors; single sign-on

- Rule suggestions, plain-English rules, anomaly alerts, earned limits with ceilings

- Agency workspaces, oversight reports, partial discovery of unregistered agents

Handover

- Technical documentation, runbooks, architecture records

### Deliverables

- Stable production

- Next-version plan based on customer data

### Done when

- 30 days without critical incidents

# 8. Feature Backlog

Must = needed for launch · Should = planned for version 1 if time allows · Later = after launch

| Area | Feature | Priority | Phase |
| --- | --- | --- | --- |
| Accounts | Login, organizations, invitations | Must | 2 |
| Accounts | Roles and approval routing | Must | 4 |
| Accounts | Single sign-on, user provisioning | Later | 6 |
| Agents | Registry, scoped tokens, kill switch | Must | 2 |
| Agents | Partial discovery of unregistered agents | Later | 6 |
| Monitoring | Observe mode, activity log, audit trail | Must | 2 |
| Monitoring | Coverage score, run timeline, OpenTelemetry import | Must | 3 |
| Rules | Visual builder, tool permissions, conditions | Must | 2 |
| Rules | Unknown tools ask a human by default | Must | 2 |
| Rules | Templates, policy replay | Should | 4 |
| Rules | Plain-English rules, rule suggestions | Later | 6 |
| Limits | Per-action and cumulative limits, idempotency | Must | 2 |
| Limits | AI-cost budgets, loop detection | Must | 3 |
| Limits | Reserve-then-settle for money | Should | 4 |
| Approvals | Dashboard, Slack, secure email; parameter locking; approver checks | Must | 2 |
| Approvals | Two-person approval | Should | 4 |
| Approvals | Teams, mobile | Later | 6 |
| Responses | Response checkpoint | Must | 3 |
| Responses | Approved-answers library | Later | 6 |
| Connections | REST API, SDKs, n8n nodes, Make app | Must | 2 |
| Connections | AI-model gateway, MCP gateway | Must | 3 |
| Connections | LangGraph, OpenAI Agents SDK | Should | 3 |
| Connections | CrewAI, Claude Agent SDK, Zapier | Later | 6 |
| Vault | Vault + Stripe, Slack, HubSpot | Must | 4 |
| Vault | Shopify, Gmail (after reviews) | Should | 4–6 |
| Vault | Salesforce, Zendesk, Outlook, databases | Later | 6 |
| Risk | Untrusted-content risk rule; risk checks can only raise risk | Should | 3 |
| Risk | Anomaly alerts, earned limits with ceilings | Later | 6 |
| Compliance | Audit export, retention settings | Must | 4 |
| Compliance | Oversight reports, regional hosting, certification | Later | 6 |

# 9. Data Model and API

## 9.1 Main data

| Entity | Key fields |
| --- | --- |
| Organization | name, settings (failure behaviour, retention, region) |
| User | organization, email, role, approver rights |
| Agent | name, platform, owner, environment, status |
| Agent token | agent, scopes, expiry, revoked |
| Rule | name, version, conditions, scope, enabled |
| Limit | scope (action / customer / resource / agent / organization), type (cost / money), period, value |
| Action event | standard action event (section 3.2) |
| Approval | event, parameter fingerprint, status, approver, channel, expiry |
| Credential | connector, encrypted secret, scopes |
| Audit entry | actor, action, target, time, chained hash |

## 9.2 Public API

| Method | Endpoint | Purpose |
| --- | --- | --- |
| POST | /v1/check | Submit an action (optional idempotency key; AgentGuard also builds one from the action); returns allow / block / pending |
| GET | /v1/approvals/{id} | Approval status |
| POST | /v1/events | Report completed actions |
| POST | /v1/actions/{connector}/{action} | Execute through the vault (enforced) |
| GET/POST | /v1/agents, /v1/rules, /v1/limits | Manage agents, rules and limits |
| POST | /v1/agents/{id}/pause ¦ resume ¦ kill | Agent controls |
| POST | /v1/otel/traces | OpenTelemetry import |
| — | AI-model gateway and MCP gateway addresses | Enforced checkpoints |
| Webhook | approval.decided, limit.reached, agent.killed, alert.created | Events to customer systems |

# 10. Security and Data Protection

| Area | Measures |
| --- | --- |
| Approval integrity | Parameter locking, idempotency, cumulative limits, verified approvers, login-protected email approvals, two-person approval for high value |
| Default safety | Unknown tools ask a human; irreversible actions strict by default; automated risk checks can only raise risk |
| Credentials | Envelope encryption with cloud key management; never logged; least-privilege scopes; rotation |
| Agent tokens | Scoped, expiring, revocable; unusual use triggers alerts |
| Customer separation | Organization checks in every query plus database row-level security; separation tests |
| Data protection | Configurable logging, masking of personal data, retention limits, data-processing agreement; regional hosting planned |
| Availability | Per-action failure behaviour, redundancy across zones, backups and restore tests, status page |
| Secure development | Code review, automated security scans, secrets scanning, threat model updates each phase |
| Independent testing | External security test before launch; all high and critical issues fixed |
| Legal | Terms with clear responsibility and liability limits; privacy policy; avoid regulated data areas in version 1 |

# 11. Quality and Operations

## 11.1 Testing

| Test type | Scope | When |
| --- | --- | --- |
| Unit tests | Rules, limits, approvals, connectors | Every change (CI) |
| Integration tests | API, database, counters, rule engine, Slack/email sandboxes | Every change (CI) |
| Approval-loophole tests | Changed parameters, retries, split actions, unauthorized approvers, email link scanners | Every change (CI) |
| Compatibility tests | Gateways against OpenAI/Anthropic formats and the MCP specification | Every change + weekly |
| End-to-end tests | n8n refund approval, LangGraph agent blocked, vault refund exactly once | Nightly |
| Load and failure tests | Decision service, gateways; component outages | Phase 2 baseline, Phase 5 final |
| Acceptance | Pratik and design partners | End of each phase |

## 11.2 Operations

| Item | Plan |
| --- | --- |
| Environments | Local → development → staging → production |
| Deployment | Automated tests and build; automatic to staging; approved release to production |
| Infrastructure as code | All cloud resources defined in Terraform |
| Monitoring and alerts | Metrics, logs, traces, error tracking, uptime checks, on-call alerts |
| Backups | Daily backups, point-in-time recovery, regular restore tests |

# 12. Go-to-Market and Launch

## 12.1 First customers

- Automation agencies that build agents for clients and need to prove they are safe.

- Growing businesses whose own clients ask how their AI is controlled.

- E-commerce and support teams whose agents handle refunds and customer messages.

## 12.2 Launch plan

| Weeks | Activity |
| --- | --- |
| 1–4 | Customer interviews from System Memo’s audience; “building in public” posts |
| 9–14 | Waitlist page; content about real agent failures and how to prevent them |
| 15–30 | Private beta with design partners until launch; case studies; short demo videos |
| 29–30 | Public launch: webinar, Product Hunt, n8n and Make communities, agency partners |
| After launch | Template library, safe automation templates, agency partner program |

## 12.3 Business model (to be validated in beta)

- Free tier to start in observe mode

- Paid plans based on number of agents and governed actions

- Agency plan for managing many clients

- Note: AI-model gateway traffic and log storage have running costs; plan limits must reflect this

## 12.4 Positioning

| Alternative | Examples | Our difference |
| --- | --- | --- |
| Enterprise AI security | Zenity, Noma, Palo Alto Networks, Check Point | Simple and self-serve for agencies and growing businesses |
| Big platforms | Microsoft, AWS, Okta agent offerings | Vendor-neutral; works with n8n, Make and any framework |
| Platform-native approvals | n8n, Zapier, agent SDK features | One view, rule set, budget and audit across all platforms, plus vault |
| Monitoring tools | LangSmith, Langfuse, Helicone | We prevent and approve, not only observe |
| Gateways / connector platforms | Portkey, LiteLLM, Composio, Arcade | Full governance layer: rules, approvals, limits, responses, coverage |

# 13. Risks and Mitigations

| Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- |
| Scope grows beyond the plan | High | High | Strict priorities; change process; connectors driven by demand |
| Platforms add native approvals | High | High | Lead with cross-platform value, vault, limits and audit |
| App reviews (Google, Shopify) delayed | Medium | High | Prepare in Phase 1, submit early; launch with Stripe, Slack, HubSpot |
| Breach of stored credentials | Very high | Low | Encryption, least privilege, threat model, independent test |
| Latency or outage affects customers | High | Medium | Per-action failure behaviour, redundancy, regional deployment |
| Approval loopholes exploited | High | Medium | Parameter locking, idempotency, cumulative limits, dedicated tests |
| Agent frameworks change quickly | Medium | High | Thin connectors on open standards; compatibility tests |
| Slow adoption by smaller businesses | High | Medium | Agencies first; observe mode; templates; personal onboarding |
| Liability for missed or approved harmful actions | High | Low | Clear terms, audit trail, insurance review |
| Dependency on one lead developer | Medium | Medium | Documentation, code reviews, second developer |

# 14. Goals

These are targets to steer the work, not guarantees. They will be reviewed after the beta.

| Area | Goal | Target |
| --- | --- | --- |
| Technical | Decision time for customers in the same region (95% of requests) | under 50 ms |
| Technical | Gateway added delay, excluding optional response checks (95% of requests) | under 30 ms |
| Technical | Platform availability | 99.9% |
| Product | Time to connect a first agent in observe mode | under 10 minutes |
| Product | Design partners using the product weekly | 10 or more by week 24 |
| Product | Share of beta partners’ money actions on enforced checkpoints | majority by launch |
| Business | Design partners converting to customers after launch | majority of active partners |
| Quality | Critical production issues in the first 30 days | none open longer than 24 hours |

# 15. Open Decisions

| # | Decision | Needed by |
| --- | --- | --- |
| 1 | Final product name and domain | Phase 0 |
| 2 | First use case and first customer group | Week 2 |
| 3 | Govern existing agents only, or also safe agents we build | Week 2 |
| 4 | Backend language and cloud provider | Week 3 |
| 5 | Second developer joining from Phase 2 | Week 4 |
| 6 | Business model and plan limits | Week 20 |
| 7 | Terms of service, liability, privacy policy | Week 26 |
| 8 | Support and maintenance arrangement after launch | Week 28 |

# Appendix – Glossary

| Term | Meaning |
| --- | --- |
| Checkpoint | A point where AgentGuard checks an agent’s action or response |
| Enforced / cooperative | Enforced: the action must pass through AgentGuard. Cooperative: the agent asks before acting |
| Parameter fingerprint | A unique code for the exact details of an action; approvals are locked to it |
| Idempotency key | A unique action ID that prevents the same action running twice |
| Cumulative limit | A limit on the total over time (e.g. per customer per week), not just per action |
| Credential vault | Secure storage of real API keys; AgentGuard executes approved actions |
| MCP | Model Context Protocol, an open standard for connecting agents to tools |
| Observe mode | Monitoring only; nothing is blocked |
| Coverage score | How much agent activity is enforced, cooperative or uncovered |
| Policy replay | Testing a new rule against past activity |